## Sheet1
Tasks
Start Date (2018) | End Date (2018) | Description | Duration (days)
2018-01-30 | 2018-02-01 | Sprint 1: Demonstrate manual setup of vm, containers and ycsb and finish design documents | 2
2018-02-01 | 2018-02-15 | Sprint 2(a): Implement script to automatically setup the environment and implemnt script to generate report based on the ycsb output | 14
2018-02-15 | 2018-02-26 | Sprint 2(b): Build parameter generator | 10
2018-02-27 | 2018-03-15 | Sprint 3: Build simulator to generate data | 16
2018-03-15 | 2018-04-05 | Sprint 4: Optimaze the performance and incorporate the smart aspect into scripts | 20
2018-04-05 | 2018-04-09 | Demo screencast | 4