## Sheet1
Tasks
Start Date (2018) | End Date (2018) | Description | Duration (days)
2018-01-08 | 2018-02-01 | Sprint 1: Demonstrate manual setup of vm, containers and ycsb and finish design documents | 26
2018-02-01 | 2018-02-11 | Sprint 2(a): Implement script to automatically setup the environment and implemnt script to generate report based on the ycsb output | 11
2018-02-11 | 2018-02-18 | Sprint 2(b): Build parameter generator | 7
2018-02-18 | 2018-02-25 | Sprint 3: Build simulator to generate data | 7
2018-02-25 | 2018-03-09 | Sprint 4(a): Optimaze the performance based on statistics | 12
2018-03-09 | 2018-03-16 | Sprint 4(b): regenerate the automatic scripts | 7
2018-03-16 | 2018-03-23 | Sprint 4 (c): Finalize the algorithm to use enable the automatic tuninng feature | 7
2018-03-23 | 2018-04-05 | Sprint 4 (d): if time allowed, GUN feature | 13
2018-04-05 | 2018-04-09 | Demo screencast | 4